## WORK PLAN
KOROGOCHO SLUM UPGRADING PROGRAMME / WORKPLAN - FIRST YEAR
Ref. | OBJECTIVES | OUTPUTS | ACTIVITIES | BUDGET | INDICATORS OF | LEAD AGENCY | ACTORS
ACHIEVEMENT
1. | COORDINATION AND SUPERVISION
1.1 | Technical and management services | 1.1.1 Preparatory Phase and Programme Management/Supervision | 1. Review of secondary socio-economic data to have a preliminary appreciation of Korogocho | 50000 | Baseline data report | MOLG/PMU | MOL, CCN, UN-HABITAT
|  |  | 2. Conduct reconnaissance field visit and interviews to increase the lead agencies' knowledge of Korogocho | 20000 | Field report |  | Community
|  |  | 3. Hold meetings and group discussions with stakeholders to create awareness and identify potential actors and partners | 20, 000 | Minutes, summary reports and list of contacts |  | Community, CBOs
|  |  | 4. Map actors, stakeholders and other ongoing initiatives | 50000 | List and report |  | MOL, CCN, UN-HABITAT, RC
|  |  | 5. Identify opinion leaders / Listening Survey | 61050 | Opinion leaders identified |  | Community
|  |  | 6. Hold workshops to train and sensitize opinion leaders | 121649 | Opinion leaders trained and sensitized |  | Opinion leaders
|  |  | 7. Election of Residents Committee (RC) | 47000 | RC elected |  | Community, Opinion leaders
|  |  | 8. Hold workshops to sensitize and train RC | 441200 | RC trained, sensitized and operationalized |  | RC
|  |  | 9. Organize a Work Plan Harmonization Retreat | 143740 | Draft harmonized Work Plan |  | MOL, CCN, UN-HABITAT
|  |  | Sub-total Preparatory Phase and Programme Management/Supervision | 934639
|  | 1.1.3 Technical Assistance | 1. Hire of consultants when required | 2500000 | Consultants hired | MOLG/PMU
|  |  | Sub-total Technical Assistance | 2500000
|  |  | Sub-total technical and management services | 3434639
1.2 | Studies, research and evaluations | 1.2.1 Situation Analysis/Socio Economic Survey | 1. Design of database, methodology and questionnaire for socio-economic survey and enumeration | 420000 | Database, methodology and questionnaire designed | UN-HABITAT | MOLG/PMU, MOL, CCN
|  |  | 2. Hold technical meetings to review and agree on database design, methodology and questionnaire | 140000 | Minutes, summary reports, data collection tools designed |  | MOLG/PMU, MOL, CCN
|  |  | 3. Design, field test and commissioning of GIS, coding forms, tables and queries | 420000 | GIS designed and tested |  | MOLG/PMU, MOL, CCN
|  |  | 4. Provide training on GIS to officers of MOLG, MOL, CCN | IN KIND | Training on GIS provided |  | MOLG/PMU, MOL, CCN
|  |  | 5. Collect and review existing socio-economic data and identify gaps | 420000 | Existing socio-economic data collected and reviewed |  | MOLG/PMU, MOL, CCN
|  |  | 6. Identify field collection team and hold training workshops | 560000 | Field collection team selected and trained |  | MOLG/PMU, MOL, CCN, RC
|  |  | 7. Collect socio-economic field data and conduct enumeration survey | 980000 | Field data and enumeration survey report |  | MOLG/PMU, MOL, CCN, RC
|  |  | 8. Verify socio economic data and enumeration survey | 420000 | Socio economic data and enumeration survey reviewed, Report |  | MOLG/PMU, MOL, CCN, RC
|  |  | 9. Data entry into the database and analysis | 840000 | Digital database updated and analysis report |  | MOLG/PMU, MOL, CCN
|  |  | 10. Prepare a draft report on socio-economic data and enumeration survey | 420000 | Situation analysis draft report |  | MOLG/PMU, MOL, CCN
|  |  | 11. Hold stakeholders workshops to present the report for approval | 140000 | Minutes and summary reports |  | MOLG/PMU, MOL, CCN, RC
|  |  | 12. Finalize the report | 175000 | Final report |  | MOLG/PMU, MOL, CCN
|  |  | Sub-total Situation Analysis/Social Economic Survey | 4935000
|  | 1.2.2 Physical Mapping | 1. Compilation of a map covering project area and its environs | 10000 | Draft map of project area and environs | MOLG/PMU | MOL, RC, CCN, UN-HABITAT
|  |  | 2. Hold field visits to draft the perimeter boundary plan of the project area | 20000 | Analysis report, draft perimeter boundary plan |  | MOL, RC, CCN, UN-HABITAT
|  |  | 3. Hold stakeholders meetings to agree and define the perimeter boundary of the project area | 20000 | Minutes, summary reports, perimeter boundary map as agreed by stakeholders |  | MOL, RC, CCN, UN-HABITAT
|  |  | 4. Start correspondence with MOL/Commissioner of Lands to establish ownership of Korogocho land | 10000 | Report on correspondence with MOL/Commissioner of Lands |  | MOL
|  |  | 5. Collect and review existing/available survey and mapping data (aerial photography, satellite imagery) and reconciliation of the data into one system | 300000 | Report and draft map with available data |  | MOL, CCN, UN-HABITAT
|  |  | 6. Evaluate the accuracy, completeness and relevance of the reconciliation of the available survey and mapping data and identify gaps requiring new data | 100000 | Report and draft Base-maps compiled from existing data |  | MOL, CCN, UN-HABITAT
|  |  | 7. Procure new mapping data (if necessary) and reconciliation with existing mapping (Alternatively procure survey instruments) | 1000000 | New maps procured, draft Base-maps updated |  | MOL, CCN, UN-HABITAT
|  |  | 8. Process newly acquired mapping and reconciliation with existing Base-maps (Alternatively procure survey instruments) | 500000 | New draft maps |  | MOL, CCN, UN-HABITAT
|  |  | 9. Conduct field surveys to edit, complete and update the draft Base-maps | 1540000 | Field data, report |  | MOL, CCN, UN-HABITAT
|  |  | 10. Entry the field data into the draft Base-map and finalize the Base-maps | 100000 | Base-maps |  | MOL, CCN, UN-HABITAT
|  |  | 11. Link the Socio-economic and enumeration database and the Base-maps into GIS | 500000 | Functional GIS |  | MOL, CCN, UN-HABITAT
|  |  | 12. Prepare thematic maps as required by various users | 500000 | Thematic maps, Final report |  | MOL, CCN, UN-HABITAT
|  |  | 13. Maintain GIS and regular update | 500000 | GIS maintained and updated |  | MOL, CCN, UN-HABITAT
|  |  | Sub-total Physical Mapping | 5100000
|  | 1.2.3 Sustainable Integrated Development Plan | 1. Publish intention to plan in the newspapers | 100000 | Newspaper article published | MOL | MOLG, CCN, UN-HABITAT
|  |  | 2. Procure equipments, softwares and setting up of the GIS | 3060000 | GIS station set up | MOL | MOLG, CCN, UN-HABITAT
|  |  | 3. Hold stakeholders meetings to discuss and agree on services and improvements required | 140000 | Minutes and summary reports | UN-HABITAT | MOLG, CCN, MOL, RC
|  |  | 4. Hold technical consultation meetings to design a draft layout of the development plans | 140000 | Minutes and summary reports | UN-HABITAT | MOLG, CCN, MOL, RC
|  |  | 5. Prepare a draft layout of the development plans | 150000 | Draft Development Plans | MOL | MOLG, CCN, UN-HABITAT
|  |  | 6. Hold consultation meetings/discussion forums to present and agree on the draft development plans | 140000 | Minutes and summary reports | UN-HABITAT | MOLG, CCN, MOL, RC
|  |  | 7. Organize internal technical consultation meetings within UN-HABITAT to share lessons learned and good best practices, and to establish linkages with other on-going activities | IN KIND | Minutes and summary reports | UN-HABITAT
|  |  | 8. Finalize the layout of the development plans | 150000 | Development Plans finalized | MOL | MOLG, CCN, UN-HABITAT
|  |  | 9. Develop a financing plan to cost the works and define the time frame | 910000 | Financing plan developed with cost estimates and implementation schedule | UN-HABITAT | MOLG, CCN, MOL
|  |  | 10. Convene a developers consultation forum with donors | 1050000 | Minutes and summary reports, Commitment for funding | UN-HABITAT | MOLG, CCN, MOL, RC
|  |  | 11. Hold consultation meetings/discussion forums to present and agree on the financing plan | 350000 | Minutes and summary reports | UN-HABITAT | MOLG, CCN, MOL, RC
|  |  | 12. Finalize the financing plan | 140000 | Financing plan finalized | UN-HABITAT
|  |  | 13. Publish notice of completion of the development plans (await comments for 60 days) | 200000 | Legal notice | MOL | MOLG, CCN, UN-HABITAT
|  |  | 14. Incorporate comments in the plans | 150000 | Plans finalized | MOL | MOLG, CCN, UN-HABITAT
|  |  | 15. Submit plans to the Minister of Lands for approval | NIL | Plans approaved | MOL | MOLG, CCN, UN-HABITAT
|  |  | 16. Notice of approval | 200000 | Legal notice | MOL
|  |  | 17. Political launch of plans | 200000 | Plan launched | MOL | MOLG, CCN, UN-HABITAT
|  |  | Sub-total Sustainable Integrated Development Plan (MOL) | 4210000
|  |  | Sub-total Sustainable Integrated Development Plan (UN-HABITAT) | 2870000
|  |  | Sub-total Sustainable Integrated Development Plan (MOL+UN-HABITAT) | 7080000
|  |  | Sub-total Studies, Research and Evaluations | 17115000
|  |  | TOTAL COORDINATION AND SUPERVISION | 20549639
2. | TRAINING AND CAPACITY BUILDING
2.1 | Training cost and materials | 2.1.1 Alternative Land Tenure | 1. Organize 3 sensitization workshops on land tenure issues | 1000000 | Workshops organized | MOL | MOLG, CCN, UN-HABITAT, RC
|  |  | Sub-total Alternative Land Tenure | 1000000
|  | 2.1.2 Community Planning and Organization | 1. Conduct capacity needs assessment consultatively | 1050000 | Report | UN-HABITAT | NGOs, RC, MOLG, CCN, Training institutions
|  |  | 2. Prepare a capacity building plan based on assessment's results | 350000 | Capacity building plan with costs and time frame |  | NGOs, RC, MOLG, CCN, Training institutions
|  |  | 3. Conduct capacity building sessions | 2170000 | Planned capacity building sessions delivered |  | NGOs, RC, MOLG, CCN, MOL, Training institutions
|  |  | Sub-total Community Planning and Organization | 3570000
|  |  | Sub-total Training Cost and Materials | 4570000
2.2 | Capacity building | 2.2.1 Support to Ministries | 1. Procure NO. 1 large format scanner for MOLG | 800000 | 1 scanner procured | MOLG/PMU
|  |  | 2. Repair of large format printer in MOLG | 50000 | 1 printer repaired
|  |  | 3. Procure extenal hard-disks (No. 4), flashdisks(No. 4), camera (No. 4) for the survey team | 100000 | Equipment purchased
|  |  | 4. Operationalize the NCC office at Housing Development Department | 568400 | Office operationalized |  | CCN
|  |  | Sub-total Support to Ministries | 1518400
|  | 2.2.2 Support to Community | 1. Develop information, dissemination and public awareness materials to spread the benefits of the Programme impact and results | 500000 | Information material developed, community sensitized and mobilized | MOLG/PMU | RC, MOL, UN-HABITAT, CCN
|  |  | 2. Hold meetings, barazas, group discussions, radio talk shows and theatre plays to create awareness and ensure community participation, cooperation and mobilization | 300000 | Community sensitized and mobilized |  | RC, MOL, UN-HABITAT, CCN
|  |  | 3. Operationalize the RC office (construction) | 700000 | RC office operationalized, report with photographs |  | RC
|  |  | 4. Hiring of personnel for RC office | 230400 | Personnel for RC office hired |  | RC
|  |  | 5. Design the RC Constitution | 50000 | RC constitution designed |  | RC
|  |  | 6. Registration of the RC | 5000 | RC's Registration Certificate |  | RC
|  |  | 7. Registration RC' s members | 50000 | RC's members registered |  | RC
|  |  | 8. Introduction of RC to the Community | 45000 | Photographs, reports |  | RC, MOL, UN-HABITAT, CCN
|  |  | Sub-total Support to Community | 1880400
|  |  | Sub-total Capacity building | 3398800
|  |  | TOTAL TRAINING AND CAPACITY BUILDING | 7968800
4. | EQUIPMENT
4.1 | Equipment for participating Ministries | 4.1.1 Equipment for participating Ministries | 1. Procure equipment for NCC office at Housing Development Department | 889100 | Equipment purchased | MOLG/PMU | CCN
| and Beneficiaries |  | Sub-total Equipment for Participating Ministries | 889100
|  | 4.1.2 Equipment for beneficiary (CBOs and FBOs) | 1. Procure equipment for RC office | 700000 | Equipment purchased | MOLG/PMU | RC
|  |  | Sub-total Equipment for beneficiary (CBOs and FBOs) | 700000
|  |  | TOTAL EQUIPMENT | 1589100
5. | ACTIVITIES
5.1 | Works and contracts | 5.1.1 Procurement of various materials | 1. Procure material for construction of foot bridge connecting high ridge residents and Dandora across Nairobi River | 1400000 | Construction material purchased | CCN | MOLG, UN-HABITAT, MOL, RC
|  |  | Sub-total Procurement of Various Materials | 1400000
|  | 5.1.2 Direct Labour Works | 1. Direct labour works for construction of foot bridge connecting high ridge residents and Dandora across Nairobi River | 600000 | Foot bridge built | CCN | MOLG, UN-HABITAT, MOL, RC
|  |  | Sub-total Direct Labour Works | 600000
|  | 5.1.3 Community contracts | 1. Hire of community labour force for construction of foot bridge | 200000 | Community labour force hired | CCN | MOLG, UN-HABITAT, MOL, RC
|  |  | Sub-total Community Contracts | 200000
|  |  | TOTAL ACTIVITIES | 2200000
|  |  | GRAND TOTAL | 32307539

## IMPLEMENTATION SCHEDULE
KOROGOCHO SLUM UPGRADING PROGRAMME / IMPLEMENTATION SCHEDULE - FIRST YEAR
Ref. | Ref. | OBJECTIVES | OUTPUTS | ACTIVITIES | INDICATORS OF | LEAD AGENCY |  |  |  |  | 2 | 0 | 0 | 8 | [20 empty] | 2 | 0 | 0 | 9
[5 empty] | ACHIEVEMENT |  | Oct |  |  |  | Nov |  |  |  | Dec |  |  |  | Jan |  |  |  | Feb |  |  |  | March |  |  |  | Apr |  |  |  | May |  |  |  | June |  |  |  | July |  |  |  | Aug |  |  |  | Sep
1. | 1. | COORDINATION AND SUPERVISION |  |  |  |  | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4 | 1 | 2 | 3 | 4
1.1 | 1.1 | Technical and management services | 1.1.1 Preparatory Phase | 1. Review of secondary socio-economic data to have a preliminary appreciation of Korogocho | Baseline data report | MOLG/PMU | bar: Oct 1 to Oct 2
|  |  |  | 2. Conduct reconnaissance field visit and interviews to increase the lead agencies' knowledge of Korogocho | Field report | bar: Oct 1 to Oct 2
|  |  |  | 3. Hold meetings and group discussions with stakeholders to create awareness and identify potential actors and partners | Minutes, summary reports and list of contacts | bar: Oct 3 to Oct 4
|  |  |  | 4. Map actors, stakeholders and other ongoing initiatives | List and report | bar: Oct 4 to Nov 1
|  |  |  | 5. Identify opinion leaders / Listening Survey | Opinion leaders identified | bar: Nov 1 to Nov 2
|  |  |  | 6. Hold workshop to train and sensitize opinion leaders | Opinion leaders trained and sensitized | bar: Nov 2 to Nov 3
|  |  |  | 7. Election of Residents Committee (RC) | RC elected | bar: Nov 3 to Nov 4
|  |  |  | 8. Hold workshops to sensitize and train RC | RC trained, sensitized and operationalized | bar: Nov 3 to Nov 4
|  |  |  | 9. Organize a Work Plan Harmonization Retreat | Draft harmonized Work Plan | bar: Nov 3 to Nov 4
1.1 |  |  | 1.1.3 Technical Assistance | 1. Hire of consultants when required | Consultants hired | MOLG/PMU
1.2 | 1.2 | Studies, research and evaluations | 1.2.1 Situation Analysis/Socio Economic Survey | 1. Design of database, methodology and questionnaire for socio-economic survey and enumeration | Database, methodology and questionnaire designed | UN-HABITAT | bar: Oct 1 to Oct 4
|  |  |  | 2. Hold technical meetings to review and agree on database design, methodology and questionnaire | Minutes, summary reports, data collection tools designed | bar: Oct 3
|  |  |  | 3. Design, field test and commissioning of GIS, coding forms, tables and queries | GIS designed and tested
|  |  |  | 4. Provide training on GIS to officers of MOLG, MOL, CCN | Training on GIS provided | bar: Dec 3 to March 2
|  |  |  | 5. Collect and review existing social-economic data and identify gaps | Existing social-economic data collected and reviewed | bar: Oct 1 to Oct 4
|  |  |  | 6. Identify field collection team and hold training workshops | Field collection team selected and trained | bar: Oct 2 to Nov 1
|  |  |  | 7. Collect socio-economic field data and conduct enumeration survey | Field data and enumeration survey report | bar: Nov 1 to Nov 4
|  |  |  | 8. Verify socio economic data and enumeration survey | Socio economic data and enumeration survey reviewed, Report | bar: Nov 4 to Dec 1
|  |  |  | 9. Data entry into the database and analysis | Digital database updated and analysis report | bar: Nov 1 to Jan 4
|  |  |  | 10. Prepare a draft report on socio-economic data and enumeration survey | Situation analysis draft report | bar: Jan 4 to Feb 2
|  |  |  | 11. Hold stakeholders workshops to present the report for approval | Minutes | bar: Feb 2 to Feb 3
|  |  |  | 12. Finalize the report | Final report | bar: Feb 3 to March 1
|  |  | 1.2.2 Physical Mapping | 1. Compilation of a map covering project area and its environs | Draft map of project area and environs | MOLG/PMU | bar: Oct 1 to Oct 2
|  |  |  | 2. Hold field visits to draft the perimeter boundary plan of the project area | Analysis report, draft perimeter boundary plan | bar: Oct 2 to Oct 4
|  |  |  | 3. Hold stakeholders meetings to agree and define the perimeter boundary of the project area | Minutes, summary reports, perimeter boundary map as agreed by stakeholders | bar: Oct 4 to Nov 2
|  |  |  | 4. Start correspondence with MOL/Commissioner of Lands to establish ownership of Korogocho land | Report on correspondence with MOL/Commissioner of Lands | bar: Oct 1 to Oct 4
|  |  |  | 5. Collect and review existing/available survey and mapping data (aerial photography, satellite imagery) and reconciliation of the data into one system | Report and draft map with available data | bar: Nov 1 to Nov 4
|  |  |  | 6. Evaluate the accuracy, completeness and relevance of the reconciliation of the available survey and mapping data and identify gaps requiring new data | Report and draft Base-maps compiled from existing data | bar: Dec 1 to Dec 2
|  |  |  | 7. Procure new mapping data (if necessary) and reconciliation with existing mapping (Alternatively procure survey instruments) | New maps procured, draft Base-maps updated | bar: Dec 3 to Jan 2
|  |  |  | 8. Process newly acquired mapping and reconciliation with existing Base-maps (Alternatively procure survey instruments) | New draft maps | bar: Jan 3 to Feb 1
|  |  |  | 9. Conduct field surveys to edit, complete and update the draft Base-maps | Field data, report | bar: Feb 2 to Feb 3
|  |  |  | 10. Entry the field data into the draft Base-map and finalize the Base-maps | Base-maps | bar: Feb 3 to March 1
|  |  |  | 11. Link the Socio-economic and enumeration database and the Base-maps into GIS | Functional GIS | bar: March 1 to March 4
|  |  |  | 12. Prepare thematic maps as required by various users | Thematic maps, Final report | bar: March 3 to Sep 4
|  |  |  | 13. Maintain GIS and regular update | GIS maintained and updated | bar: Jan 1 to Sep 4
|  |  | 1.2.3 Sustainable Integrated | 1. Publish intention to plan in the newspapers | Newspaper article published | MOL | bar: March 1 to March 2
|  |  | Development Plan | 2. Procure equipments, softwares and setting up of the GIS | GIS station set up | MOL | bar: Oct 1 to Dec 4
|  |  |  | 3. Hold stakeholders meetings to discuss and agree on services and improvements required | Minutes and summary reports | UN-HABITAT | bar: March 3 to March 4
|  |  |  | 4. Hold technical consultation meetings to design a draft layout of the development plans | Minutes and summary reports | UN-HABITAT | bar: Apr 1 to Apr 2
|  |  |  | 5. Prepare a draft layout of the development plans | Draft Development Plans | MOL | bar: Apr 2 to Apr 4
|  |  |  | 6. Hold consultation meetings/discussion forums to present and agree on the draft development plans | Minutes and summary reports | UN-HABITAT | bar: Apr 4 to May 1
|  |  |  | 7. Organize internal technical consultation meetings within UN-HABITAT to share lessons learned and good best practices, and to establish linkages with other on-going activities | Minutes and summary reports | UN-HABITAT | bar: Apr 3 to May 1
|  |  |  | 8. Finalize the layout of the development plans | Development Plans finalized | MOL | bar: May 1 to May 3
|  |  |  | 9. Develop a financing plan to cost the works and define the time frame | Financing plan developed with cost estimates and implementation schedule | UN-HABITAT | bar: May 2 to May 4
|  |  |  | 10. Convene a developers consultation forum with donors | Minutes and summary reports, Commitment for funding | UN-HABITAT | bar: May 4 to June 1
|  |  |  | 11. Hold consultation meetings/discussion forums to present and agree on the financing plan | Minutes and summary reports | UN-HABITAT | bar: June 2 to June 3
|  |  |  | 12. Finalize the financing plan | Financing plan finalized | UN-HABITAT | bar: June 3 to June 4
|  |  |  | 13. Publish notice of completion of the development plans (await comments for 60 days) | Legal notice | MOL | bar: June 1 to July 4
|  |  |  | 14. Incorporate comments in the plans | Plans finalized | bar: Aug 1 to Aug 3
|  |  |  | 15. Submit plans to the Minister of Lands for approval | Plans approaved | MOL | bar: Aug 4
|  |  |  | 16. Notice of approval | Legal notice | MOL | bar: Sep 2
|  |  |  | 17. Political launch of plans | Plan launched | MOL | bar: Sep 3 to Sep 4
2. | 2. | TRAINING AND CAPACITY BUILDING
2.1 | 2.1 | Training cost and materials | 2.1.1 Alternative Land Tenure | 1. Organize 3 sensitization workshops on land tenure issues | Workshops organized | MOL | bar: Oct 3 to Oct 4; Apr 1 to Apr 2; Sep 3 to Sep 4
|  |  | 2.1.2 Community Planning and | 1. Conduct capacity needs assessment consultatively | Report | UN-HABITAT | bar: Oct 1 to Oct 4
|  |  | Organization | 2. Prepare a capacity building plan based on assessment's results | Capacity building plan with costs and time frame | bar: Nov 1 to Nov 3
|  |  |  | 3. Conduct capacity building sessions | Planned capacity building sessions delivered | bar: Nov 4 to Sep 4
2.2 | 2.2 | Capacity building | 2.2.1 Support to Ministries | 1. Procure NO. 1 large format scanner for MOLG | 1 scanner procured | MOLG/PMU | bar: Oct 1 to Oct 4
|  |  |  | 2. Repair of large format printer in MOLG | 1 printer repaired | bar: Oct 1 to Oct 2
|  |  |  | 3. Procure extenal hard-disks (No. 4), flashdisks (No. 4), camera (No. 1) for the survey team | Equipment purchased | bar: Oct 1 to Oct 2
|  |  |  | 4. Operationalize the NCC office at Housing Development Department | Office operationalized | bar: Nov 1 to March 4
|  |  | 2.2.2 Support to Community | 1. Develop information, dissemination and public awareness materials to spread the benefits of the Programme impact and results | Information material developed, community sensitized and mobilized | MOLG/PMU
|  |  |  | 2. Hold meetings, barazas, group discussions, radio talk shows and theatre plays to create awareness and ensure community participation, cooperation and mobilization | Community sensitized and mobilized
|  |  |  | 3. Operationalize the RC office (construction) | RC office operationalized, report with photographs | bar: Oct 1 to Dec 4
|  |  |  | 4. Hiring of personnel for RC office | Personnel for RC office hired
|  |  |  | 5. Design the RC Constitution | RC constitution designed | bar: Nov 4 to Dec 1
|  |  |  | 6. Registration of the RC | RC's Registration Certificate | bar: Dec 2 to Dec 3
|  |  |  | 7. Registration RC' s members | RC's members registered | bar: Dec 4 to Sep 4
|  |  |  | 8. Introduction of RC to the Community | Photographs, minutes | bar: Nov 4 to Dec 1
2. | 4. | EQUIPMENT
2.1 | 4.1 | Equipment for participating Ministries and Beneficiaries | 4.1.1 Equipment for participating Ministries | 1. Procure equipment for NCC office at Housing Development Department | Equipment purchased | MOLG/PMU
|  |  | 4.1.2 Equipment for beneficiary (CBOs and FBOs) | 1. Procure equipment for RC office | Equipment purchased | MOLG/PMU
2. | 5. | ACTIVITIES
2.1 | 5.1 | Works and contracts | 5.1.1 Procurement of various materials | 1. Procure material for construction of foot bridge connecting high ridge residents and Dandora across Nairobi River | Construction material purchased | CCN | bar: Oct 1 to Oct 4
|  |  | 5.1.2 Direct Labour Works | 1. Direct labour works for construction of foot bridge connecting high ridge residents and Dandora across Nairobi River | Foot bridge built | CCN | bar: Nov 1 to March 4
|  |  | 5.1.3 Community contracts | 1. Hire of community labour force for construction of foot bridge | Community labour force hired | CCN | bar: Nov 1 to March 4